## GanttChard(Dev-Summarized)
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
| October |  | November |  |  |  |  | December
Time/Task | 2015-10-19 | 2015-10-26 | 2015-11-02 | 2015-11-09 | 2015-11-16 | 2015-11-23 | 2015-11-30 | 2015-12-07 | 2015-12-14 | 2015-12-21 | 2015-12-28
Create Sentiment Analyzer Module | bar: 2015-10-19 to 2015-10-26
Create Word Normalizer | bar: 2015-11-02 to 2015-11-16
Create Learner Module | bar: 2015-11-16 to 2015-11-30
Recalibrate Relational Inference Analyzer | bar: 2015-11-23 to 2015-12-14
Modules Integration | bar: 2015-12-21 to 2015-12-28

## Progress(Dev-Summarized)
PROGRESS SHEET
Thesis Title: | Inappropriate Expressions Recognition using Bootstrapping as Semi-Supervised Learning
Members: | Joshua S. Dapitan | Section: | BSCS 4-2
Anjanette R. Lasala
Task at Hand |  |  | Start Date | Date Ended | No. of Days Delayed | Status | Remarks
Create Sentiment Analyzer Module |  |  | 2015-10-19 | 2015-10-17 |  | Early Finished | Sentiment Analysis with Graphs, needs Stemmer because cannot Access other Words
Create Word Normalizer |  |  | 2015-11-02 |  |  |  | Stemmer Tool? Ditch out in Phase
Create Learner Module |  |  | 2015-11-16 |  |  |  | Very long
Recalibrate Relational Inference Analyzer |  |  | 2015-11-23 |  |  |  | Very long
Modules Integration |  |  | 2015-12-21