## ProgressSheet
Inappropriate Expressions Recognition using Bootstrapping as SemiSupervised Learning
Start Date | Task at Hand | Date Ended | Done? | Remarks?
2015-10-19 | Prepare SentiAnalyzer
2015-10-26 | Prepare SentiAnalyzer-For WordNet Definitions
2015-11-02 | Create WordNet Referencer-Collect InappExp Not in WordNet
2015-11-09 | Create Word Normalizer
2015-11-16 | Create Word Normalizer
2015-11-23 | Calibrate Learning Module-Calibrate Linear Treshold
2015-11-30 | Recalibrate Relational Inference Analyzer-Prepare WordSense Polarity Analzer via InappExp Feature Sets
2015-12-07 | Recalibrate Relational Inference Analyzer
2015-12-14 | Create Word Naïve Bayes Polarity Analyzer
2015-12-21 | Create Word Naïve Bayes Polarity Analyzer
2015-12-28 | Modules Integration
2016-01-04 | Modules Integration
2016-01-11 | Collection of test data
2016-01-18 | Collection of test data
2016-01-25 | Chapter 4 Start
2016-02-01 | Chapter 4 Writing
2016-02-08 | Chapter 4 Writing/Chapter 5 Writing
2016-02-15 | Chapter 5 Writing/#RoadToColloquium
2016-02-22 | Chapter 5 Writing
2016-02-29 | Chapter 5 Writing/Publishable Paper Writing
2016-03-07 | Abstract Writing/Publishable Paper Writing
2016-03-14 | Thesis Defense?
2016-03-21 | Thesis Defense?

## GanttChart
Time /Task | 2015-10-19 | 2015-10-26 | 2015-11-02 | 2015-11-09 | 2015-11-16 | 2015-11-23 | 2015-11-30 | 2015-12-07 | 2015-12-14 | 2015-12-21 | 2015-12-28 | 2016-01-04 | 2016-01-11 | 2016-01-18 | 2016-01-25 | 2016-02-01 | 2016-02-08 | 2016-02-15 | 2016-02-22 | 2016-02-29 | 2016-03-07 | 2016-03-14 | 2016-03-21
Prepare SentiAnalyzer | bar: 2015-10-19
Prepare SentiAnalyzer-For WordNet Definitions | bar: 2015-10-26
Create WordNet Referencer-Collect InappExp Not in WordNet | bar: 2015-11-02
Create Word Normalizer/Learner Module | bar: 2015-11-09
Create Word Normalizer/Learner Module | bar: 2015-11-16
Calibrate Learning Module-Calibrate Linear Treshold | bar: 2015-11-23
Recalibrate Relational Inference Analyzer-Prepare WordSense Polarity Analzer via InappExp Feature Sets | bar: 2015-11-30
Recalibrate Relational Inference Analyzer | bar: 2015-12-07
Create Word Naïve Bayes Polarity Analyzer | bar: 2015-12-14
Create Word Naïve Bayes Polarity Analyzer | bar: 2015-12-21
Modules Integration | bar: 2015-12-28
Modules Integration | bar: 2016-01-04
Collection of test data | bar: 2016-01-11
Collection of test data | bar: 2016-01-18
Chapter 4 Start | bar: 2016-01-25
Chapter 4 Writing | bar: 2016-02-01
Chapter 4 Writing/Chapter 5 Writing | bar: 2016-02-08
Chapter 5 Writing/#RoadToColloquium | bar: 2016-02-15
Chapter 5 Writing | bar: 2016-02-22
Chapter 5 Writing/Publishable Paper Writing | bar: 2016-02-29
Abstract Writing/Publishable Paper Writing | bar: 2016-03-07
Thesis Defense? | bar: 2016-03-14
Thesis Defense? | bar: 2016-03-21

## GanttChard(Dev-Summarized)
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
| October |  | November |  |  |  |  | December
Time/Task | 2015-10-19 | 2015-10-26 | 2015-11-02 | 2015-11-09 | 2015-11-16 | 2015-11-23 | 2015-11-30 | 2015-12-07 | 2015-12-14 | 2015-12-21 | 2015-12-28
Create Sentiment Analyzer Module | bar: 2015-10-19 to 2015-10-26
Create Word Normalizer | bar: 2015-11-02 to 2015-11-16
Create Learner Module | bar: 2015-11-16 to 2015-11-30
Recalibrate Relational Inference Analyzer | bar: 2015-11-23 to 2015-12-14
Modules Integration | bar: 2015-12-21 to 2015-12-28